## Sheet1
| Sr Dev | Jr Dev | UX | Post MVP
Authority frontend - wireframes (1 day) | 1
Authority frontend - UX design - Figma (3 days) |  |  | 3
Authority frontend - UI - minimal (14 days) |  | 14
Authority backend - engine - registration (3 days) | 3
Authority backend - engine - election (2 days) | 2
Authority backend - engine - tests (2 days) | 2
Authority backend - API (2 days) | 2
Authority backend - store (1 day) | 1
Authority backend - authentication (4 days) | 4
Device frontend - engine - election / authority (5 days) | 5
Device frontend - engine - block negotiation (6 days) | 6
Device frontend - engine - block submission (3 days) | 3
Device frontend - engine - whisper / whitelist / blacklist (3 days) | 3
Device frontend - engine - p2p wrapper (2 days) | 2
Device frontend - engine - own verification (3 days) | 3
Device frontend - engine - election verification (14 days) | 14
Device frontend - engine - tests (5 days) | 5
Device frontend - local store (5 days) | 5
Device frontend - wireframes (3 days) | 3
Device frontend - UX design - Figma (4 days) |  |  | 4
Device frontend - UI - minimal (14 days) |  | 14
Device frontend - UI - aesthetical (28 days) |  |  |  | 28
| 64 | 28